## KT From Georges
Category | Task | Completion% | Remarks | Refinitiv Team | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10
General | Overview about ZawyaOnEikon | 100% |  | Georges | bar: 2019-12-09
ZawyaOnEikon | Functional Component overview | 100% |  | Georges | bar: 2019-12-09
| Technical Component overview | 75% |  | Georges | bar: 2019-12-09; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27
| Sample Company Screener | 100% |  | Georges | bar: 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27
| Search Filter | 100% |  | Georges | bar: 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2019-12-31
| Sample Excel download | 100% |  | Georges | bar: 2020-01-03; 2020-01-06 to 2020-01-07
| App Hits | 0% | Stas find the issue. It is related to my access. Stas need some time to fix this. | Stas | bar: 2020-01-08
| Eikon Desktop | 0% | Installation is geeting failed. It seems like due to network issue installation is getting failed. | Eikon App server support/Surajit
| JET Library | 0% |  | Georges
| PDF | 100% |  | Georges | bar: 2020-01-01 to 2020-01-02
| Integration/Interfaces deep drive | 0% | This subject line is dependent on VS2013 installation | Georges
| Code setup | 85% | This subject line is dependent on VS2013 installation VS2015 installation done on 20th Dec and code setup completed. Windows Setup is pending as it is dependent on Confluence/Jira Access. A ticket(RITM2079461) has been raised on 11th Dec | Surajit, Georges | bar: 2019-12-10; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27
Tools/ Utilities | Install GIT | 100% |  | Surajit | bar: 2019-12-10
| Install Eikon App Engine | 100% |  | Surajit | bar: 2019-12-11
| Install Tortoise | 100% |  | Surajit | bar: 2019-12-10
| Get Visual Studio 2013 license | 100% |  | TR Support Team | bar: 2019-12-12 to 2019-12-13
| Install Visual Studio 2013 | 100% | INC2868436, PR#332370, TASK#1948998 Installed VS2015 on 20th Dec. | TR Support Team | bar: 2019-12-11 to 2019-12-13; 2019-12-16 to 2019-12-20
| Jira/Confluence Access | 0% | bar: 2019-12-12 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24; 2019-12-26 to 2019-12-27; 2019-12-30 to 2020-01-03; 2020-01-06
| GIT repo Access | 100% |  | Georges | bar: 2019-12-11
Assignment | Work Assignment (as Shadow) | 0% |  | Georges
| Primary ownership for Project Assignment | 0% |  | Georges
TRBD | bar: 2019-12-09 to 2020-01-02
General | Overview about TRBD | 0% |  | Rizalito
TRBD | Functional Component overview | 0% |  | Rizalito
| Technical Component overview | 0% |  | Rizalito
| Code deep drive | 0% |  | Rizalito
| Integration/Interfaces deep drive | 0% |  | Rizalito
| Code setup | 50% |  | Surajit, Rizalito | bar: 2020-01-08 to 2020-01-09
Tools/ Utilities |  | 0% |  | Surajit
|  | 0% |  | TR Support Team
|  | 0% |  | Rizalito
Assignment | Work Assignment (as Shadow) | 0% |  | Rizalito
| Primary ownership for Project Assignment | 0% |  | Rizalito