## KT From Georges
Category | Task | Completion% | Remarks | Refinitiv Team | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11
ZawyaOnEikon Backend | bar: 2020-01-10 to 2020-02-03
General | Overview about ZawyaOnEikon Backend - Kickoff | 100% |  | Georges,Smarak,Alok,Surajit | bar: 2020-01-10
ZawyaOnEikon | Functional Component overview | 0% |  | Georges,Smarak
| Technical Component overview | 0% |  | Georges,Smarak
| Integration/Interfaces deep drive | 0% |  | Georges,Smarak
| Local Code setup-ZawyaContent | 50% | Downloaded code from SVN and doing the set up with George | Georges,Smarak | bar: 2020-01-10
Tools/ Utilities | 1. Tortoise SVN 2. IntelliJ 3. JBoss-as-7.1.1 4. Java -JDK 1.6 5. Maven 6. JRebel 7. FileZilla | 100% | Jrebel not yet installed | Georges,Smarak
| Jira/Confluence Access | 100% | VDI not yet access to Alok. | Georges,Smarak
| GIT/SVN repo Access | 100% | VDI not yet access to Alok. | Georges,Smarak
Assignment | Work Assignment (as Shadow) | 0% |  | Georges
| Primary ownership for Project Assignment | 0% |  | Georges
TRP and BRI Backend | bar: 2020-01-10 to 2020-02-03
General | Overview about TRP and BRI backend products and Architecture | 100% | TRP / BRI Backend / BRI Free / MENA Projects which all share common infrastructure. | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin | bar: 2020-01-10
TRP and BRI | Functional Component overview | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
| Technical Component overview | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
| Code deep drive | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
| Integration/Interfaces deep drive | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
| Code setup | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
Tools/ Utilities | TRP Environment Setup - 2 docs shared - (.NET and Java/Coldfusion Part) | 100% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin | bar: 2020-01-10
| Local code setup | 0% | will start today with help of Tinawi | Tinawi,Smarak
| TRP API Local Environment Setup | 0% |  | Hao, Lester Pani, Smarak Tinawi, Mohammad M. Alok Sah Li, Haoni Li, Justin
Assignment | Work Assignment (as Shadow) | 0% |  | Tinawi
| Primary ownership for Project Assignment | 0% |  | Tinawi